## Sheet1
Ecommerce Store Relaunch Planner
Phase | Task | Owner | Due Date | Status | Priority | Notes
Phase 1: Pre-relaunch audit (6–8 weeks before)
Phase 1 | Audit the current site; document all live pages, URLs, and top-traffic pages. |  |  | To do | High
Phase 1 | Export the current sitemap and save it for redirect mapping. |  |  | To do | High
Phase 1 | Identify your top 20 pages by traffic using analytics. |  |  | To do | High
Phase 1 | Benchmark current conversion rate, bounce rate, and revenue. |  |  | To do | High
Phase 1 | List all third-party integrations and apps in use. |  |  | To do | Medium
Phase 1 | Audit the existing product catalog; flag outdated listings. |  |  | To do | Medium
Phase 1 | Review the current email list and customer account data. |  |  | To do | Medium
Phase 1 | Document the current SEO rankings for target keywords. |  |  | To do | High
Phase 2: Build & migration (4–6 weeks before)
Phase 2 | Set up the new store/redesign it in a staging environment. |  |  | To do | High
Phase 2 | Migrate the product catalog to the new store/design. |  |  | To do | High
Phase 2 | Recreate or update all key pages (Home, About, FAQs, Policies). |  |  | To do | High
Phase 2 | Configure payment gateways and test transactions. |  |  | To do | High
Phase 2 | Set up and test all shipping methods and rates. |  |  | To do | High
Phase 2 | Reconnect email marketing and automation flows. |  |  | To do | Medium
Phase 2 | Reconnect analytics (GA4, pixels, heatmap tools). |  |  | To do | High
Phase 2 | Test all product pages, cart, and checkout end-to-end. |  |  | To do | High
Phase 3: SEO & URL management (2–4 weeks before)
Phase 3 | Create a 301 redirect map for every changed URL. |  |  | To do | High | Redirect old URL → new URL
Phase 3 | Set up all redirects in the new store before go-live. |  |  | To do | High
Phase 3 | Update internal links to point to new URLs. |  |  | To do | High
Phase 3 | Verify meta titles and descriptions on all key pages. |  |  | To do | Medium
Phase 3 | Submit updated sitemap to Google Search Console. |  |  | To do | High | Do this day of launch
Phase 3 | Set canonical tags correctly on all pages. |  |  | To do | Medium
Phase 3 | Check that structured data/schema markup is intact. |  |  | To do | Medium
Phase 4: Customer communication (1–2 weeks before)
Phase 4 | Draft a relaunch announcement email for existing customers. |  |  | To do | Medium
Phase 4 | Prepare social media posts announcing the relaunch. |  |  | To do | Medium
Phase 4 | Update the Google Business Profile if store info has changed. |  |  | To do | Low
Phase 4 | Notify any active affiliates or partners of the relaunch date. |  |  | To do | Low
Phase 4 | Prepare a maintenance/coming soon page if going offline briefly. |  |  | To do | Medium
Phase 4 | Plan a relaunch offer or incentive for returning customers. |  |  | To do | Medium
Phase 5: Go-live & post-launch review
Phase 5 | Point domain to new store/push redesign live. |  |  | To do | High
Phase 5 | Test checkout flow on live store immediately after launch. |  |  | To do | High
Phase 5 | Verify all redirects are working on the live store. |  |  | To do | High
Phase 5 | Monitor analytics and error logs for the first 48 hours. |  |  | To do | High
Phase 5 | Send relaunch announcement email to customer list. |  |  | To do | High
Phase 5 | Publish social media relaunch announcement. |  |  | To do | Medium
Phase 5 | Check Google Search Console for crawl errors after 7 days. |  |  | To do | High
Phase 5 | Compare post-launch metrics to pre-relaunch benchmarks at Day 30. |  |  | To do | Medium